## Sheet1
Week | Day | Hours | Description
1 | 2023-08-31 | 1 | Orientation Video and Quiz
| 2023-08-31 | 1 | Discussing project with Professor Gross
| 2023-08-31 | 4 | Proposal Form, Intake Form
2 | 2023-09-07 | 3 | Researching Debian, Computer Cluster, ssh
| 2023-09-07 | 1 | Discussing research topics with Professor Gross
| 2023-09-08 | 2 | ssh to computers, exploring the software
| 2023-09-09 | 3 | Research NFS
| 2023-09-10 | 2 | Research NIS
3 | 2023-09-11 | 4 | Design Documentation
| 2023-09-13 | 4 | Researching /etc/shadow, sftp, grep, openMPI
| 2023-09-14 | 1.5 | Meeting with Professor Gross, getting root priveleges on one of the computers
| 2023-09-14 | 1 | Looking through the changelog on Palma
4 | 2023-09-18 | 3 | Setting up repository and PM Board
|  | 1.5 | Backup Config files
|  | 1.5 | Update to the Latest Release Point bullseye 11.7
| 2023-09-19 | 2 | Trying to fix broken package dependencies
| 2023-09-21 | 3 | Meeting professor Gross, installing bullseye 11.7 from scratch
| 2023-09-23 | 4 | More research, installing ubuntu on personal laptop for SSH
5 | 2023-09-26 | 6 | Setup dual boot Windows-Ubuntu at home
| 2023-09-28 | 2.5 | Meeting with professor Gross, cloning the hard drive
| 2023-09-29 | 3.5 | Looking through config files for NIS, more research
| 2023-10-01 | 3 | Demo 1 Video, Installing software to make a video
6 | 2023-10-02 | 1 | Demo 1 Presentation, TimeLog and PM updates
| 2023-10-04 | 5 | NIS Research, NIS Setup on Palma
| 2023-10-05 | 3 | Meeting with professor Gross, verifying the functionality of NIS
| 2023-10-07 | 6 | NFS Research, NFS Setup on Palma, Testing functionality
7 | 2023-10-09 | 5 | Going through the old changelog, making my new changelog
| 2023-10-11 | 6 | Setting up a Virtual Machine on a home computer for potential tests
| 2023-10-13 | 2 | OpenMPI research
| 2023-10-15 | 8 | Software Setup on home computers attempting to mimic Brooklyn College Cluster Setup
8 | 2023-10-16 | 7 | Software Setup on home computers attempting to mimic Brooklyn College Cluster Setup
| 2023-10-18 | 6 | Software Setup on home computers attempting to mimic Brooklyn College Cluster Setup
| 2023-10-20 | 2 | Verifying the software on Palma
| 2023-10-22 | 4 | openMPI setup, openMPI testing, CUDA Research
9 | 2023-10-23 | 6 | CUDA Research, openMPI Research, openMPI sample code
| 2023-10-26 | 3 | meeting with Professor Gross, installing NVIDIA Drivers, installing CUDA Toolkit
| 2023-10-27 | 6 | Researching CUDA, working on writing sample code
10 | 2023-10-30 | 4 | PowerPoint familiarization, started making slides
| 2023-11-02 | 2 | meeting with Professor Gross, progress checking, planning the next steps
| 2023-11-04 | 8 | AWK Research, practice scripts, working on PowerPoint presentation
| 2023-11-06 | 2 | Power Pont finishing touches, submission
11 | 2023-11-09 | 3 | Meeting with professor Gross
| 2023-11-10 | 4 | Finishing work on Palma
| 2023-11-11 | 8 | Changelog update, Metis and Gomera Cleanup
12 | 2023-11-13 | 2 | Power Point work
| 2023-11-16 | 3 | Meeting with professor Gross, Metis cloning
| 17-Nov-19-Nov | 10 | Resolving issues with passwords, verifying work
13 |  |  | Break/College closed
14 | 2023-11-30 | 3 | Meeting with professor Gross
| 31-Nov | 3 | Metis Cleanup
| 1-Dec-4-Dec | 4 | Finishing work + PowerPoint
15 | 2023-12-07 | 1 | Meeting with professor Gross
| 2023-12-12 | 3 | Final Presentation
| 2023-12-13 | 5 | Finishing Presentation Slides+ Video